## Sheet1
| WDD_Project_2024 | Done Y/N? | Team Member
Week | Goals for this week
week 8
| read brief & be familiar with it | y
| brainstorm with group - what is website like | y
| team member strengths and weaknesses | y
| 1 person creates a shared folder and shares it! | y
my own wireframe
| sitemap for whole website | y
week 9 | use wireframe to code up page | y
| think about class and id names so no-one overwrites anothers CSS! | y
| decide who does the form/gallery/minigame | y
| decide website content | y
| record who contributed - meeting and coding | y
| Let Emer know if someone is out of contact | y
week 10 | add your tasks and assign them to a team member | y
| implement css | y
| add images | y
| further discuss topics | y
| choose a theme | y
| Let Emer know if someone is out of contact | y
week 11 | add your tasks and assign them to a team member | y
| experiment with layout | y
| simplefy/fix code | y
| Let Emer know if someone is out of contact | y
week 12 | finish up code
deploy website
testing - functional testing, speed test
Write/record report
only one CSS file - if possible more marks
testing menu links work
images in a folder - at least 4
form - must have 5 fields, JS validation
comments in HTML, CSS and JS
| Make sure the author name is on each webpage | y
| everyone has DOM manipulation on their own webpage | y
Submission | SUNDAY 8th DEC 9pm
Antonio